## Test Report Ridwan v1.0.2
Tracking ID | Module/Sub Module/Feature | Build Version/URL | Platfrom | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | QA Remarks | Attachments | Issue Status-Developers Feedback | Developer's Remark | Reporting Manager's Feedback | Current Iteration | Issue Occurance Count | Developer Name | Defect Solved Date
1 | Favourtite | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: When there is no favourite quotes it shows a message "No Data Found" Steps: 1. Open the app. 2. Click Favourtite | CR | GUI Error | Medium | Decision Pending | Ridwan | It doesn't look appropritate
2 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: Remaining time is not accurate. Steps: 1. Open the app. 2. Click on Remaining time. | Bugs | Calculation Errors | High | Open | Ridwan
3 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: Previous button "<" is not working. Steps: 1. Open the app. 2. Click on the previous button on the top left corner in the image section | Bugs | Functionality Errors | High | Open | Ridwan | If we tap on the left side on image it swipes ..but In the home page image slider, left side of the image is not woking. Note: It is woking in category, favourite. Just not working in home page
4 | Home > Today's Prayer Times | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: Present Waqt should be highlighted. Steps: 1. Open the app. 2. Click on the previous button on the top left corner in the image section | CR | GUI Error | Medium | Decision Pending | Ridwan | Suggesgtions: When Dhuhr Waqt is running, It should highlight Or color the Specific waqt. Ex: As Screenshot image, If Dhuhr 11:56 AM- 04:33 PM was Highlighted separately It may looked good. N.B: Left time also missing
5 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: Location Button is not woking Steps: 1. Open the app. 2. Click on Location (Dhaka) | Bugs | Functionality Errors | High | Open | Ridwan
6 | Menu > Review | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: Review star is not clickable and 3rd star and 5th star color is same.. It may look good if these colors are not same. Steps: 1. Open the app. 2. Click on Menu 3. Click on Review | CR | GUI Error | Medium | Decision Pending | Ridwan
7 | Home > Today's Prayer Times | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: Left time is not showing. Steps: 1. Open the app. 2. Click on Today's Prayer Times. | Bugs | Functionality Errors | High | Open | Ridwan
8 | Menu | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: Riseup Labs logo is not redirecting to it's website after clicking. Steps: 1. Open the app. 2. Click on Menu | Bugs | Functionality Errors | High | Open | Ridwan | In the about section riseup labs logo is redirecting but it is not redirecting in Menu section.
9 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: There should be a section of forbidden prayer times. | CR | Functionality Errors | High | Decision Pending | Ridwan | There are some forbidden times at Morning,Noon,Evening which should be add in the app Note: I have added a sample pic of another app as reference in the attachments..
10 | Notifications | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: For Asr prayer No notification appeared. | Bugs | Functionality Errors | High | Solved | Ridwan | Note: All notifications permission was allowed. Update: Asr Magrib and Isha notification appeared
11 | Menu>About | 1.0.2 | Device: Samsung A20 Andriod version: Andriod 10 | 2023-05-16 | Issue Name: The facebook, youtube, instagram logo color should be accurate, and the size should be more precise. Step: 1.Click on menu. 2.Click on about. | CR | Functionality Errors | High | Open | Ridwan
12 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: Dropdown symbol may look good if it matches with questions font color | Fine Tuning | GUI Error | Medium | Open | Ridwan | While dropdown is down, it may look good if its color is black.. And while up, color should be green as picture
13 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: It may look good If there is a section of Hijri date as this is an Islamic app. | CR | Functionality Errors | Medium | Decision Pending | Ridwan
14 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name:It may look good If there is a section for Tasbih count | CR | Functionality Errors | Medium | Decision Pending | Ridwan
15 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: It may look good If there is a section for kiblah compass | CR | Functionality Errors | Medium | Decision Pending | Ridwan
16 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: It may look good If there is a section of Sehri and Iftar time | CR | Functionality Errors | Medium | Decision Pending | Ridwan
17 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: It may look good If there is a translatror function to translate in Bangla. | CR | Functionality Errors | Medium | Decision Pending | Ridwan
18 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: It may look good If there is a options in the settings for theme selection such as dark mode or light mode. | CR | Functionality Errors | Medium | Decision Pending | Ridwan
19 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: When user minimize tha app and opens the app after 1 hour, Time section in the app not updates.. | Bugs | Functionality Errors | High | Open | Ridwan | In the video time is 06:38 pm and Magrib Waqt already started. but in the video we can see Asr waqt is running and it shows remainin time 05:00 minutes
20 | Home | 1.0.2 | Device: Samsung A20 Andriod version: Andriod 10 | 2023-05-16 | Issue Name: If I click on location continuously, the screen blinks, and the location name language is changed from English to Bangla and Bangla to English. Steps: 1.Click on location continously. | Bugs | Functionality Errors | High | Open | Ridwan
21 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: There is a "more" button which can be removed as it has no special functionality. | Fine Tuning | GUI Error | High | Open | Ridwan | In the screenshot, When user click on the dashboard, It redirects to "Today's Prayer Times" page. but when we click "more" button on the dashboard it is doing the same thing. So it may look good if "more" button is removed.
22 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 10 | 2023-05-16 | Issue Name: If there should start time, reather than left of remaining time it could be more meaningful. | CR | Functionality Errors | High | Open | Ridwan
23 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: There is a shadow in the next and previous button area which not looks user friendly | CR | GUI Error | High | Decision Pending | Ridwan
24 | Menu>Names od Allah | 1.0.2 | Device: Samsung A20 Andriod version: Andriod 10 | 2023-05-16 | Issue Name: 85 number name is not fully visible(In English) | Bugs | Functionality Errors | High | Open | Ridwan | There should be more padding in previous version like android 10.
25 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: Multi touch response is not working properly | Bugs | GUI Error | High | Open | Ridwan | It only works for single touch
26 | Menu > General Question' | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: Dropdown doesn't work properly sometimes. | Bugs | GUI Error | High | Open | Ridwan | fourth question answer is not showing but dropdown symbol is showing dropup sign
27 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: When favourite button is clicked multiple times It starts to stop work. It becomes unclickable | Bugs | Functionality Errors | High | Open | Ridwan | For first image favourite button is already clicked.. Can't unfavourite it but for the second image it is working fine
28 | Home | 1.0.2 | Device: Motorola Edge Plus Andriod version: Andriod 12 | 2023-05-16 | Issue Name: App Crashes | Bugs | Functionality Errors | High | Open | Ridwan | App already crashed 3 times while testing.. Please watch video carefully.. This is how app can be crashed. N.B: I did gorilla testing
29 | Menu>About | 1.0.2 | Device: Samsung A20 Andriod version: Andriod 10 | 2023-05-16 | Issue Name:In the about section, the version name should be merged with the about column, and there should be more padding for the app version name. | Fine Tuning | Functionality Errors | Medium | Open | Ridwan | The padding is okay in android 12 but not in android 10.
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425