## App
Tracking ID | Module/Sub Module/Feature | Build Version/URL | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | QA Remarks | Attachments | Reporting Manager's Feedback | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date
1 | Attendance |  | 2022-11-01 | Full name in the name field is not showing. Text field should wrap the text | Bugs | Functionality Errors | High | Solved | Ridwan
2 | Attendance |  | 2022-11-01 | By default No data is showing in Attendance Report | Bugs | Functionality Errors | High | Solved | Ridwan
3 | Attendance |  | 2022-11-01 | Absent Students are not showing in the attendance report | Bugs | Functionality Errors | High | Solved | Ridwan
4 | Attendance |  | 2022-11-01 | In attendance report students name are showing last to first. List should same as Daily attendance list | Bugs | Functionality Errors | Medium | Solved | Ridwan
5 | Attendance |  | 2022-11-01 | Can not give attendance of previous date | Bugs | Functionality Errors | Medium | No Action | Ridwan
6 | Personal Info |  | 2022-11-01 | Education Qualification dropdown field name is not showing | Fine Tuning | Functionality Errors | Medium | Solved | Ridwan
7 | Admission status |  | 2022-11-01 | Dropdown field name is not showing except "Enrolment date of LUL ABL models" | Fine Tuning | Functionality Errors | Medium | Solved | Ridwan
8 | Child Occupation |  | 2022-11-01 | Dropdown field name is not showing except "Employer" | Fine Tuning | Functionality Errors | Medium | Solved | Ridwan
9 | Child Occupation |  | 2022-11-01 | Can not edit "Type of work" and "Duration of work" | Bugs | Functionality Errors | High | Solved | Ridwan
10 | Health Information |  | 2022-11-01 | Can not save health information data | Bugs | Functionality Errors | High | Solved | Ridwan
11 | Attendance |  | 2022-11-01 | If students status is selected present and we click on the name then Absent note is showing. Absent Note will only show when the attendance status is absent | CR | Functionality Errors | Medium | No Action | Ridwan
12 | Attendance |  | 2022-11-01 | While editing attendance button name should be "Edit Attendance" | Fine Tuning | Functionality Errors | High | Solved | Ridwan
13 | Attendance |  | 2022-11-01 | While re submitting attendance button name should be "Re Submit" | Fine Tuning | Functionality Errors | High | Solved | Ridwan
14 | Attendance |  | 2022-11-01 | After re submitting attendance, Message should show "Attendance Updated Successfully" | Fine Tuning | Functionality Errors | High | Solved | Ridwan
15 | Attendance |  | 2022-11-02 | Please change the name of "absent note" to "Remarks" | Fine Tuning | Functionality Errors | High | Failed | Ridwan |  |  |  | 1 | 1
16 | M&E |  | 2022-11-02 | If suggestions day is 10+ then user can pick any date | Bugs | Functionality Errors | High | Solved | Ridwan
17 | M&E |  | 2022-11-02 | Add edit option to the observe page | CR | Functionality Errors | High | Open | Ridwan
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425