## App (1.2)
Tracking ID | Module/Sub Module/Feature | Build Version/URL | Testing Date | Attachments | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | QA Remarks | Reporting Manager's Feedback | Developer's comment | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date | *
1 | Login | 1.2 | 2023-02-14 |  | "Actual Result: The app has been crashed/the screen has been black after clicking the 'Login' button more times. Steps To Reproduce: 1. open the app 2. go to the Login 3. Fill in the username & password section with invalid credentials. 4. Click the 'Login' button more times. Expected Result: The App should not be crashed. | Bugs | Functionality Errors | High | Open | Ridwan | After clicking 'ok' button of error message few times later it is redirect to login page. | [5 empty] | Solved |  | 2023-02-19
2 | Login | 1.2 | 2023-02-09 |  | Actual Result: There isn't any space between "Login/Registration button" and blue line. Steps To Reproduce: 1. open the app 2. go to the Login/Registration section Expected Result:There should've a space between "Login/Registration button" and blue line. | Fine Tuning | GUI Error | Medium | Open | Ridwan | It is showing in Bluestacks But it is working fine in physical device. | [5 empty] | Solved |  | 2023-02-19
3 | Login | 1.2 | 2023-02-09 |  | Actual Result: The field name "USER NAME" is not appropriate. Steps To Reproduce: 1. open the app 2. go to the Login section Expected Result:The field name "USERNAME/EMAIL" is more appropriate. | Fine Tuning | GUI Error | Medium | Open | Ridwan | [6 empty] | Solved |  | 23-20-2023
4 | Login | 1.2 | 2023-02-09 |  | Actual Result: In USER NAME field, Placeholder is asking for email. It is showing "Enter your Email" Steps To Reproduce: 1. open the app 2. go to the Login section Expected Result: In USER NAME field, Placeholder should ask for USERNAME. It should show "Enter Your USERNAME." | Fine Tuning | GUI Error | Medium | Open | Ridwan | [6 empty] | Solved |  | 23-20-2023
5 | Login | 1.2 | 2023-02-09 |  | Actual Result: The text color used for placeholder and field name is not looking appropriate. Steps To Reproduce: 1. open the app 2. go to the Login section Expected Result: Fieldname text color should be dark/deep and placeholder text color should be light/grey. | Fine Tuning | GUI Error | Medium | Open | Ridwan | [6 empty] | Solved |  | 2023-02-28
6 | Login | 1.2 | 2023-02-09 |  | Actual Result: In PASSWORD field,when eye icon turned off the password is showing for a moment before turning into a dot. Steps To Reproduce: 1. open the app 2. go to the Login section Expected Result: When eye icon is turned off, While typing password it shouldn't be visible for a moment too. It should show only dot. | Fine Tuning | GUI Error | Medium | Open | Ridwan | [6 empty] | Solved |  | 2023-02-23
7 | Login | 1.2 | 2023-02-09 |  | Actual Result: The Button name "Restore Password" is not preferable. Steps To Reproduce: 1. open the app 2. go to the Login section Expected Result:The button name "Forgot Password" is more preferable. | Fine Tuning | GUI Error | Low | Open | Ridwan | [6 empty] | Solved |  | 2023-02-28
8 | Login | 1.2 | 2023-02-09 |  | Actual Result: The placeholder text in Password field is slightly inappropriate. Steps To Reproduce: 1. open the app 2. go to the Login section Expected Result:The text in Password placeholder is should be "Enter Your PASSWORD/Password" | Fine Tuning | GUI Error | Low | Open | Ridwan | [6 empty] | Solved |  | 2023-02-28
9 | Login | 1.2 | 2023-02-09 |  | Actual Result: When Username/Password is clicked it still shows the text in the placeholder. Steps To Reproduce: 1. open the app 2. go to the Login section Expected Result: When Username/Password is clicked it shouldn't show the text in the placeholder. It should show only cursor. | Fine Tuning | GUI Error | Medium | Open | Ridwan | [6 empty] | Solved | i will do it in future | 2023-02-28
10 | Login | 1.2 | 2023-02-09 |  | Actual Result: While user typing password there is a message showing "Password minimum charcter is 8" "Password must include at least one Uppercase letter" "Password must include at least one lowercase letter" "Password must include at least one special character" "Password must include at least one number" "Password maximum character is 20" Steps To Reproduce: 1. open the app 2. go to the Login section Expected Result: While typing password there shouldn't be any message. | Fine Tuning | GUI Error | Medium | Open | Ridwan | In login Page user is logging in with his registered account. So It shouldn't show this types of suggestion while typing password. | [5 empty] | Solved |  | 2023-02-19
11 | Login | 1.2 | 2023-02-10 |  | "Actual Result: The user can scroll the login page. Steps To Reproduce: 1. open the app 2. go to the Login section 3. Scroll down the screen. Expected Result: The login page should not be scrollable. | Bugs | Functionality Errors | High | Open | Ridwan | It should be user friendly. | [5 empty] | Solved |  | 2023-02-28
12 | Login | 1.2 | 2023-02-09 |  | Actual Result: Restore password doesn't work. It gives a message "Email setting is incomplete." Steps To Reproduce: 1. open the app 2. go to the Login section. 3. Tap on Restore password. Expected Result: Email seeting should work properly. | Bugs | Functionality Errors | Medium | Open | Ridwan | [6 empty] | Solved |  | 2023-02-19
13 | Registration > Username | 1.2 | 2023-02-09 |  | Actual Result: While typing in username, there is a message showing "Username minimum character is 5" Steps To Reproduce: 1. Open the app 2. Go to the Registration section. Expected Result: Username field may not need boundary limitations. | CR | Functionality Errors | Medium | Decision Pending | Ridwan | If there is a minimum limitation of 5 letter then user whose names are small. Such as: Zim,akib, abir,emon They can't put their name as username. So username minimum boundary limitations should be 2 letters | [5 empty] | Solved |  | 2023-02-28
14 | Login/Registration | 1.2 | 2023-02-09 |  | Actual Result: While scrolling up/down the header drops. It is not user friendly. Steps To Reproduce: 1. Open the app 2. Go to the Login/Registration section. Expected Result: The header should be more user friendly and It shouldn't drop while scroll. | Bugs | GUI Error | Medium | Open | Ridwan | [6 empty] | Solved |  | 2023-02-23
15 | Login/Registration | 1.2 | 2023-02-09 |  | Actual Result: In login section Username and Password name is fully written in Capital letter but In Registration Section, Username and password is written in mixedup format (Capital and small) Steps To Reproduce: 1. Open the app 2. Go to the Login/Registration section. Expected Result: In both section there should be one forrmat only | Fine Tuning | GUI Error | Medium | Open | Ridwan | [6 empty] | Solved |  | 2023-02-23
16 | Login | 1.2 | 2023-02-09 |  | Actual result: There is no confirmation message "Successfully Login" STP: 1. open the app 2. go to the Registration section 3. Fill all the field 4. press submit button Expected result: it should appear a pop-up message "Successfully Login" | Fine Tuning | GUI Error | Low | Solved | Ridwan | [6 empty] | Solved |  | 2023-05-02
17 | Registration | 1.2 | 2023-02-09 |  | Actual result: it takes invalid mobile number STP: 1. open the app 2. go to the Registration section 3. Give the phone number Expected result: it shouln't take the invalid number | Bugs | Data validation | High | Solved | Ridwan | Invalid phone number | [5 empty] | Solved |  | 2023-05-02
18 | Registration | 1.2 | 2023-02-09 |  | Actual result: confirmation message Need to be visible more STP: 1. open the app 2. go to the Registration section 3. Fill all the field 4. press submit button Expected result: it should visible more a pop-up message "Successfully registration" | Fine Tuning | GUI Error | Low | No Action | Ridwan | [6 empty] | Solved |  | 2023-05-02
19 | Registration > Username | 1.2 | 2023-02-09 |  | Actual Result: In Username field, there is taking more than one words as input Steps To Reproduce: 1. Open the app 2. Go to the Registration section. Expected Result: Username shouldn't be more than one word. | Bugs | Functionality Errors | Medium | Open | Ridwan | [6 empty] | Solved |  | 2023-05-02
20 | Registration > Phone | 1.2 | 2023-02-09 |  | Actual Result: In Phone field, there is taking 14 digits as input. Steps To Reproduce: 1. Open the app 2. Go to the Registration section. Expected Result: In phone field, There shouldn't take more than 11 digits as input. | Bugs | Functionality Errors | Medium | Open | Ridwan | [6 empty] | Solved |  | 23-20-2023
21 | Registration > Name | 1.2 | 2023-02-09 |  | Actual Result: In Name field, Numbers/Special characters are taking as an input Steps To Reproduce: 1. Open the app 2. Go to the Registration section. Expected Result: In Name field, Only alphabets should take as an input. | Bugs | Functionality Errors | Medium | Open | Ridwan | [6 empty] | Solved |  | 23-20-2023
22 | Registration > Email | 1.2 | 2023-02-09 |  | Actual Result: In Email field, Wrong email format is taking as an input Steps To Reproduce: 1. Open the app 2. Go to the Registration section. Expected Result: In Email field, Only right valid email format should take as an input. | Bugs | Functionality Errors | Medium | Open | Ridwan | in email field user can register their account with this type of email 1@gmail.com a@gmail.com sdsa@gmail.com.. these are not valid emails. So while account registration users email should be valid email | [5 empty] | Solved |  | 23-20-2023
23 | Registration > Organization | 1.2 | 2023-02-09 |  | Actual Result: In Organization field, numbers/special character is taking as an input Steps To Reproduce: 1. Open the app 2. Go to the Registration section. Expected Result: An organization name can't be numbers/special characters only. So it should take alphabets or (mixed of alphabets and numbers) as an input only. | Bugs | Functionality Errors | Medium | Open | Ridwan | [6 empty] | Solved |  | 23-20-2023
24 | Registration | 1.2 | 2023-02-09 |  | Actual Result: When we click on a particular field, it still shows the text in the placeholder. Steps To Reproduce: 1. open the app 2. go to the Login section Expected Result: After clicking on a field It shouldn't show the text in the placeholder. It should show only cursor. | Fine Tuning | GUI Error | Medium | Open | Ridwan | [6 empty] | Solved |  | 23-20-2023
25 | Registration > Age | 1.2 | 2023-02-09 |  | Actual Result: In the age field the maximum age to select is 40 Steps To Reproduce: 1. open the app 2. go to the Login section Expected Result: In the age field the maximum age to select should be 100. | Fine Tuning | GUI Error | Medium | Open | Ridwan | [6 empty] | Solved |  | 23-20-2023
26 | Restore Password | 1.2 |  |  | Actual result: 'Email setting is incomplete' is shown when the user enters the valid email & click 'Restore password'. STP: 1. open the app 2. Click the Restore password. 3. Fill the email field with valid email address(latifur.riseuplabs@gmail.com) 4. press 'Restore password' button. Expected result: Restore password section should be completed. | Bugs | Functionality Errors | High | No Action | Ridwan | [6 empty] | Solved |  | 2023-05-02
27 | Restore Password | 1.2 | 2023-02-14 |  | "Actual Result: The app has been crashed/the screen has been black after clicking the 'Restore Password' button more times. Steps To Reproduce: 1. open the app 2. Click the 'Restore password' 3. Enter valid Email 4. Click the 'Restore Password' button more times. Expected Result: The App should not be crashed/black screen. | Bugs | Functionality Errors | High | Open | Ridwan | After clicking 'ok' button of error message few times later it is redirect to Restore Password page. | [5 empty] | Solved |  | 2023-02-19
28 | My Course | 1.2 |  |  | Actual result: Font/text format are not the same(small/capital letter) of all modules in the 'My Course' section. STP: 1. open the app 2. Login with valid credentials- email: latifur.riseuplabs@gmail.com password: Uu12345678@ 3. Click the 'Continue' button. 5. See all the modules. Expected result: All module's text should be the same(small/capital letter) in the 'My Course' section. | Fine Tuning | GUI Error | Low | No Action | Ridwan | [6 empty] | Solved |  | 2023-05-02
29 | My Course | 1.2 |  |  | Actual result: Though the user clicks the 'MODULE ONE' for the first time after enrolling the 'Would you like to resume the presentation from the last slide viewed' is shown. And if the user clicks the 'yes' button it redirect to the 'Module One' last content(13 no). STP: 1. open the app 2. Login with valid credentials- email: latifur.riseuplabs@gmail.com password: Uu12345678@ 3. Click Courses and Enroll Course. 4. Click 'My course'. 5. Click 'Continue' button. 5. Click 'MODULE ONE'. 6. Click the 'Yes' button 7. See it redirect to the last content of "Module One' Expected result: 'Would you like to resume the presentation from the last slide viewed' popup message should not be shown for the first time. | Bugs | Functionality Errors | High | Solved | Ridwan | [6 empty] | Solved | this is not app end issue | 2023-02-28
30 | My Course | 1.2 |  |  | Actual result: If the user only see the last content of module ,the module is finished & user gets the permission to go to the next module. STP: 1. open the app 2. Login with valid credentials- email: latifur.riseuplabs@gmail.com password: Uu12345678@ 3. Click Courses and Enroll Course. 4. Click the 'My course'. 5. Click the 'Continue' button. 5. Click one module 6. Click the Menu button. 7.Click the last content 7. The module is finished & the 'Next module' button is visible. Expected result: The user should be completed all content of the module then the user gets permission to go to the next Module. | Bugs | Functionality Errors | High | Solved | Ridwan | Is it bug/not? Confused | [5 empty] | Solved | this is not app end issue | 2023-02-28
31 | My Course | 1.2 | 2023-02-09 |  | Actual result: In the landscape mode content number & content progress bar aren't show . STP: 1. open the app 2. Login with valid credentials- email: latifur.riseuplabs@gmail.com password: Uu12345678@ 3. Click Courses and Enroll Course. 4. Click the 'My course'. 5. Click the 'Continue' button. 5. Click one module 6. Rotate the device screen. Expected result: Content number & content progress bar should be shown in the landscape mode . | Bugs | GUI Error | Medium | Open | Ridwan | [6 empty] | Solved |  | 2023-02-28
32 | My Course | 1.2 | 2023-02-09 |  | Actual result: In the landscape mode sometimes all contents are show in the left portion of device. STP: 1. open the app 2. Login with valid credentials- email: latifur.riseuplabs@gmail.com password: Uu12345678@ 3. Click Courses and Enroll Course. 4. Click the 'My course'. 5. Click the 'Continue' button. 5. Click one module 6. Rotate the device screen. Expected result: All contents should be shown across the entire device. | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved |  | 23-20-2023
33 | My Course | 1.2 | 2023-02-09 |  | Actual result: In the menu section 'INFORMATION' & 'EXIT' option aren't clickable/worked properly. STP: 1. open the app 2. Login with valid credentials- email: latifur.riseuplabs@gmail.com password: Uu12345678@ 3. Click Courses and Enroll Course. 4. Click the 'My course'. 5. Click the 'Continue' button. 5. Click Module one 6. See some content video/Module one 7th content. 7.Click menu option from the right side top corner of this video 8. Click the 'INFORMATION' & 'EXIT' option Expected result: 'INFORMATION' & 'EXIT' option should be worked properly in the menu section. | Bugs | Functionality Errors | Medium | Open | Ridwan | [6 empty] | Solved | this is not app end issue | 2023-02-28
34 | My Course | 1.2 | 2023-02-09 |  | Actual result: Click 'HERE' is not working properly. STP: 1. open the app 2. Login with valid credentials- email: latifur.riseuplabs@gmail.com password: Uu12345678@ 3. Click Courses and Enroll Course. 4. Click the 'My course'. 5. Click the 'Continue' button. 5. Click Module one 6. See the content video/Module one 7th content. 7.Click menu option from the right side top corner of this video 8. Click the' COURSE BOOK' 9. Click 'HERE' Expected result: Click 'HERE' should be worked properly.. | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved | this is not app end issue | 2023-02-28
35 | My Course | 1.2 | 2023-02-10 |  | Actual result: The picture don't match with question. STP: 1. open the app 2. Login with valid credentials- email: latifur.riseuplabs@gmail.com password: Uu12345678@ 3. Click Courses and Enroll Course. 4. Click the 'My course'. 5.Complete all module 6. Click Take quiz Expected result: Picture should be matched with question. | Fine Tuning | GUI Error | Medium | Open | Ridwan | If the fruits picture will show in the 'Which of the following are types of fruits' then it will be better. | [5 empty] | Solved |  | 2023-02-19
36 | My Course | 1.2 | 2023-02-10 |  | Actual result: For the first time attempt in quiz section if user click the 'Preview Result' sometimes an error message is shown & if user click 'ok' button then the full screen has blank. STP: 1. open the app 2. Login with valid credentials- email: latifur.riseuplabs@gmail.com password: Uu12345678@ 3. Click Courses and Enroll Course. 4. Click the 'My course'. 5.Complete all module 6. Click Take quiz 7. Complete all quiz 8. Click the 'Preview Result' Expected result: The error message should not be occurred. | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved |  | 2023-02-19
37 | Home | 1.2 |  |  | Actual result: For newly registered user , In the home page both "See Course" button navigate to My Course page. STP: 1. open the app 2. Login with valid credentials(email & password). 3. Click the 'See Course' button. Expected result: In the home page both "See Course" button should navigate to Courses page | Bugs | Navigational Error | High | Solved | Ridwan | Navigation issue, See Courses button should navigate to Courses page for the newly registrate user | [5 empty] | Solved |  | 2023-05-02
38 | Courses > Course details > FAQ | 1.2 |  |  | Actual result: In the Course Details page FAQ module is empty STP: 1. open the app 2. Login with valid credentials(email & password). 3. Click on Courses. 4. Click on Course Details 5. Click on FAQ Expected result: In the Course Details page FAQ module should not be empty | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved |  | 2023-05-02
39 | Course > My Courses > Module 1 | 1.2 |  |  | Actual result: In Module 1 all the contents ar showing upside down. STP: 1. open the app 2. Login with valid credentials(email & password). 3. Click on My Courses. 4. Click on Continue 5. Click on Module 1 Expected result: In Module 1, all the contents should show properly so users can read easily | Bugs | Functionality Errors | High | No Action | Ridwan | In bluestack, module contents are showing upside down. It should be normal so user can read properly | [5 empty] | Solved |  | 2023-05-02
40 | Home > Course > Course Details > Curriculum | 1.2 |  |  | Actual result: Curriculum page's all modules time and Home page's all modules time does match STP: 1. open the app 2. Login with valid credentials(email & password). 3. Go to home page's coourse structure section 4. Click on the modules 5. Click on Course 6. Click on Course Details 7. Click on Curriculum Expected result: Curriculum page's all modules time and Home page's all modules time should be same | Bugs | GUI Error | Medium | Solved | Ridwan | Module time should be same in all pages. | [5 empty] | Solved |  | 2023-05-02
41 | Home > Course > Course Details > Curriculum | 1.2 | 2023-02-09 |  | Actual result: Font/text format are not the same(small/capital letter) of all modules in the ' Curriculum' section. STP: 1. open the app 2. Login with valid credentials(email & password). 3. Go to home page's coourse structure section 4. Click on the modules 5. Click on Course 6. Click on Course Details 7. Click on Curriculum Expected result: All module's text should be the same(small/capital letter) in the ' Curriculum' section. | Fine Tuning | GUI Error | Low | Open | Ridwan | It's not looking nice | [5 empty] | Solved |  | 2023-05-02
42 | Home > Course > Course Details > Overview | 1.2 | 2023-02-10 |  | Actual result: First letter of lectures is small. STP: 1. open the app 2. Login with valid credentials(email & password). 3. Click on Courses 4. Click on Course Details Expected result: First letter of lectures should be capital. | Fine Tuning | GUI Error | Low | Open | Ridwan | The word should be 'Lectures' | [5 empty] | Solved |  | 2023-02-23
43 | Home | 1.2 | 2023-02-09 |  | Actual result: In the Home pages course structure sections, Module 3's number order is not okay STP: 1. open the app 2. Login with valid credentials(email & password). 3. Go to the home page's course structure section 4. Click on the modules Expected result: In the Home pages course structure sections, Module 3's number order should start from 3.1.1 or 3.1.0 | Bugs | GUI Error | Medium | Open | Ridwan | number order should start from 3.1.1 or 3.1.0 instead of 3.1. | [5 empty] | Solved |  | 2023-02-28
44 | Home | 1.2 | 2023-02-14 |  | Actual result: In the Home pages the spelling of certificate is wrong. STP: 1. open the app 2. Login with valid credentials(email & password). 3. Go to the home page's course structure section Expected result: Spelling should not be wrong | Fine Tuning | GUI Error | Medium | Open | Ridwan | The right spelling is 'Certificate' | [5 empty] | Solved |  | 23-20-2023
45 | Profile | 1.2 | 2023-02-09 |  | Actual result: There is no "Type Current Password" option in the profile edit page for updating the password STP: 1. open the app 2. Login with valid credentials(email & password). 3. Go to the home page's course structure section 4. Click on the modules Expected result: There should be a "Type Current Password" option in the profile edit page | Bugs | Functionality Errors | Medium | Open | Ridwan | For better security there should be a option to check current password for updating the password | [5 empty] | Solved | not in a design | 2023-02-28
46 | Profile | 1.2 | 2023-02-09 |  | Actual result: The mobile number input option takes up to 14 digits. STP: 1. open the app 2. Login with valid credentials(email & password). 3. Go to edit profile. 4. Input more than 11 digits in mobile number Expected result: The mobile number input option takes only 11 digits. | Bugs | Functionality Errors | Medium | Open | Ridwan | [6 empty] | Solved |  | 2023-02-28
47 | Profile | 1.2 | 2023-02-09 |  | Actual result: In the Edit Profile page Name field is taking digit input STP: 1. open the app 2. Login with valid credentials(email & password). 3. Go to edit profile. 4. Input number in Name feild Expected result: In the Edit Profile page Name field should not take digits as input | Bugs | Functionality Errors | Medium | Open | Ridwan | [6 empty] | Solved |  | 23-20-2023
48 | Profile | 1.2 | 2023-02-09 |  | Actual Result: The text color used for placeholder and filed name is not looking appropriate. Steps To Reproduce: 1. open the app 2. Login with valid credentials(email & password). 3. Go to edit profile section. Expected Result: Fieldname text color should be dark/deep and placeholder text color should be light/grey. | Fine Tuning | GUI Error | Medium | Open | Ridwan | [6 empty] | Solved |  | 2023-02-28
49 | Profile | 1.2 | 2023-02-09 |  | Actual Result: There don't have any 'New password' & 'Re-type New Password' section & also there don't have any required icon * in the Password section. Steps To Reproduce: 1. open the app 2. Login with valid credentials(email & password). 3. Go to edit profile section. Expected Result: If there is shown 'New password' instead of Password & 'Re-type New Password' instead of Re-Type Password then it will be better & need required icon * in the password section. | CR | GUI Error | Medium | Open | Ridwan | [6 empty] | Solved |  | 2023-02-28
50 | Profile | 1.2 | 2023-02-09 |  | Actual Result: When user Change only devision without changing the previous District & Upazila then it is shown with new Division and previous devision's district & Upazila. 1. open the app 2. Login with valid credentials(email & password). 3. Go to edit profile section. 4. Select new devision 5. Click the 'Save' button 6. Go to the Edit Profile section again & see the Division, District & Upazila Section. Expected Result: User should not be changed only devision. | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved |  | 23-20-2023
51 | My Course > Continue | 1.2 | 2023-02-09 |  | Actual Result: After completing all the modules there is a Button name "Course Complete" which is clickable. But it does not navigate 1. open the app 2. Login with valid credentials(email & password). 3. Click on My course 4. Click on continue Expected Result: There should not be any Button name "Course Complete". | CR | GUI Error | Medium | Open | Ridwan | "Course Complete" should not be a button | [5 empty] | Solved |  | 2023-02-28
52 | My Course > Review Quiz | 1.2 | 2023-02-09 |  | Actual Result: After passing the quiz, in the Review Quiz section there is no option to see which answer were wrong. 1. open the app 2. Login with valid credentials(email & password). 3. Click on My course 4. Go to modules and complete the module 5. Take the quiz. 6. Go to Review Quiz Expected Result: After passing the quiz, in the Review Quiz section there should be an option to see which answer were wrong by coloring them Red | CR | GUI Error | Medium | Open | Ridwan | All the Answer is green, there should be a Red color for wrong answer | [5 empty] | Solved | there was a backend issue for this case.now its solve | 2023-02-28
53
54
55
56
57
58
59
60
61