## App (1.1)
Tracking ID | Module/Sub Module/Feature | Build Version/URL | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | QA Remarks | Attachments | Reporting Manager's Feedback | Developer's comment | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date
1 | Regestration | 1.1 | Mob Number:00000000000 | Actual result: it takes invalid mobile number STP: 1. open the app 2. go to the Registration section 3. Give the phone number Expected result: it shouln't take the invalid number | Bugs | Data validation | High | Solved | Ridwan | Invalid phone number
2 | Regestration | 1.1 | N/A | Actual result: confirmation message Need to be visible more STP: 1. open the app 2. go to the Registration section 3. Fill all the field 4. press submit button Expected result: it should visible more a pop-up message "Successfully registration" | Fine Tuning | GUI Error | Low | No Action | Ridwan
3 | Login | 1.1 | email: pappu.riseuplabs@gmail.com password: Pappu1997$% | Actual result: There is no confirmation message "Successfully Login" STP: 1. open the app 2. go to the Registration section 3. Fill all the field 4. press submit button Expected result: it should appear a pop-up message "Successfully Login" | Fine Tuning | GUI Error | Low | Solved | Ridwan
4 | Restore Password | 1.1 |  | Actual result: 'Email setting is incomplete' is shown when the user enters the valid email & click 'Restore password'. STP: 1. open the app 2. Click the Restore password. 3. press 'Restore password' button. Expected result: Restore password section should be completed. | Bugs | Functionality Errors | High | No Action | Ridwan
5 | My Course | 1.1 |  | Actual result: Font/text format are not the same(small/capital letter) of all modules in the 'My Course' section. STP: 1. open the app 2. Login with valid credentials- email: latifur.riseuplabs@gmail.com password: Uu12345678@ 3. Click the 'Continue' button. 5. See all the modules. Expected result: All module's text should be the same(small/capital letter) in the 'My Course' section. | Fine Tuning | GUI Error | Low | No Action | Ridwan
6 | My Course | 1.1 |  | Actual result: Middle module is skipped when one module is finished and the user clicks the 'Next module' button & at the time of loading if the user again click the 'Next module button. STP: 1. open the app 2. Login with valid credentials- 3. Click the 'My course'. 4. Click the 'Continue' button. 5. Finish one module. 6. Click the 'Next Module' button 7. Again click the 'Next Module' button. Expected result: No module should be skipped. | Bugs | Functionality Errors | High | Solved | Ridwan
7 | My Course | 1.1 |  | Actual result: Though the user clicks the 'MODULE ONE' for the first time after enrolling the 'Would you like to resume the presentation from the last slide viewed' is shown. And if the user clicks the 'yes' button it redirect to the 'Module One' last content(13 no). STP: 1. open the app 2. Login with valid credentials- 3. Click Courses and Enroll Course. 4. Click 'My course'. 5. Click 'Continue' button. 5. Click 'MODULE ONE'. 6. Click the 'Yes' button 7. See it redirect to the last content of "Module One' Expected result: 'Would you like to resume the presentation from the last slide viewed' popup message should not be shown for the first time. | Bugs | Functionality Errors | High | Solved | Ridwan
8 | My Course | 1.1 |  | Actual result: If the user only see the last content of module ,the module is finished & user gets the permission to go to the next module. STP: 1. open the app 2. Login with valid credentials- 3. Click Courses and Enroll Course. 4. Click the 'My course'. 5. Click the 'Continue' button. 5. Click one module 6. Click the Menu button. 7.Click the last content 7. The module is finished & the 'Next module' button is visible. Expected result: The user should be completed all content of the module then the user gets permission to go to the next Module. | Bugs | Functionality Errors | High | Solved | Ridwan | Is it bug/not? Confused
9 | Home | 1.1 |  | Actual result: For newly registered user , In the home page both "See Course" button navigate to My Course page. STP: 1. open the app 2. Login with valid credentials(email & password). 3. Click the 'See Course' button. Expected result: In the home page both "See Course" button should navigate to Courses page | Bugs | Navigational Error | High | Solved | Ridwan | Navigation issue, See Courses button should navigate to Courses page for the newly registrate user
10 | Courses > Course details > FAQ | 1.1 |  | Actual result: In the Course Details page FAQ module is empty STP: 1. open the app 2. Login with valid credentials(email & password). 3. Click on Courses. 4. Click on Course Details 5. Click on FAQ Expected result: In the Course Details page FAQ module should not be empty | Bugs | Functionality Errors | High | Open | Ridwan
11 | Course > My Courses > Module 1 | 1.1 |  | Actual result: In Module 1 all the contents ar showing upside down. STP: 1. open the app 2. Login with valid credentials(email & password). 3. Click on My Courses. 4. Click on Continue 5. Click on Module 1 Expected result: In Module 1, all the contents should show properly so users can read easily | Bugs | Functionality Errors | High | No Action | Ridwan | In bluestack, module contents are showing upside down. It should be normal so user can read properly
12 | Home > Course > Course Details > Curriculum | 1.1 |  | Actual result: Curriculum page's all modules time and Home page's all modules time does match STP: 1. open the app 2. Login with valid credentials(email & password). 3. Go to home page's coourse structure section 4. Click on the modules 5. Click on Course 6. Click on Course Details 7. Click on Curriculum Expected result: Curriculum page's all modules time and Home page's all modules time should be same | Bugs | GUI Error | Medium | Solved | Ridwan | Module time should be same in all pages.