## Test Report - App1.1
Tracking ID | Module/Sub Module/Feature | Build Version/URL | Platfrom | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | Attachment | QA Remarks | Reporting Manager's Feedback | Developer's comment | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date
1 | Whole App | Apk |  | 2023-01-04 | Issue Name: App is not rotating Actual Result: After opening the app auto rotate function is not working. Steps To reproduce: 1. Open the app Expected Result: When "Auto Rotate" button is clicked on the device app should've been rotated. | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | After opening the app, The app is not rotating perfectly. It is not user friendly.
2 | Login | Apk |  | 2023-01-04 | Issue Name: Login page heading Actual Result: In the heading part, the Login text isn't looking good & In the Login page there are no language change option button. Steps To reproduce: 1. Open the App 2. See the heading section Expected Result: In the heading part, if there are shown the app name instead of 'Login' then it will be better. If the language change option is shown from the first login page then it will be better. | CR | GUI Error | Medium | Solved | Ridwan |  | In the heading part, if there are shown the app name 'WHO/WHO E-Learning' instead of 'Login' then it will be better
3 | Login | Apk |  | 2023-01-04 | Issue Name: Alert Message Actual Result: In the login & Create new account part if user want to login & create new account with blank data, no alert message is shown. Steps To reproduce: 1. Open the App. 2. Click Login button with blank HRS ID and Password. 3. Click the Create new account 3. Click the Continue button with blank designation. Expected Result: An alert message should be shown when user want to login & create new account with blank data | Fine Tuning | GUI Error | Low | Solved | Ridwan |  | In the alert message ,If there is shown 'HRS ID, Password is required' something like that then I think it will be better.
4 | Login | Apk |  | 2023-01-04 | Issue Name: Forgot Password Actual Result: In the login page there don't have any forgot password option. Steps To reproduce: 1. Open the App 2. See the underneath of password field. Expected Result: Forgot password option should be shown underneath of password field. | Bugs | Functionality Errors | High | Solved | Ridwan |  | If the forgot password option is shown underneath the password section/Login section then it will be better.
5 | Logout | Apk |  | 2023-01-04 | Issue Name: Login session is not expiring. Actual Result: App is not logging out after closing the whole app. Steps To reproduce: 1. Enter the credential on the login page. HRS ID: 301 password:1234 2. Verify that system should redirect to the Dashboard. 3. Close the App. Expected Result: App should've been auto logged out after a particular session time and ask for re-login. | Bugs | Functionality Errors | Low | Solved | Ridwan |  | App should've logged out after closing the app. Or there can be a session time out which will automatically happen after a certain time. After that, account will be logged out automatically.
6 | Profile | Apk |  | 2023-01-04 | Issue Name: Change Password eye icon in profile module. Actual Result: When one eye icon click to show/hide the password the all eye icon change together & show/hide password together. Steps To reproduce: 1. Enter the credential on the login page. HRS ID: 301 password:1234 2. Verify that system should redirect to the Dashboard. 3. Click the profile icon. 4. Click the Change Password button. 5. Enter a password (Old Password, New Password, Confirm Password). 6. Click the eye icon 1/2 times. Expected Result: At a time one icon/password should be change. Test Data: Old Password: 1234 New Password: 2345 Confirm Password: 2345 | Bugs | Functionality Errors | High | Solved | Ridwan |  | If I want to see one password & if I click that password eye button then only that password should be shown. All password shouldn't be shown at a time when I click one eye icon.
7 | Profile | Apk |  | 2023-01-05 | Issue Name: Colons in Profile module Actual Result: In General , Change password & About Us button the colons are shown. Steps To reproduce: 1. Enter the credential on the login page. HRS ID: 301 password:1234 2. Verify that system should redirect to the Dashboard. 3. Click the profile icon. 4. See the General, Change Password, About Us button. Expected Result: The colons should not be shown in General, Change Password & About Us button. | Fine Tuning | GUI Error | Low | Solved | Ridwan |  | In General, Change Password & About Us button, the colons isn't looking so good.
8 | Profile | Apk |  | 2023-01-05 | Issue Name: Profile Picture Actual Result: The profile picture doesn't change/upload. Steps To reproduce: 1. Enter the credential on the login page. HRS ID: 301 password:1234 2. Verify that system should redirect to the Dashboard. 3. Click the profile icon. 4. Click the camera icon of profile picture. 5. Select a picture from gallery. Expected Result: Profile picture should be changed/uploaded. | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | If there is picture cropping option, I think it will be better.
9 | Profile | Apk |  | 2023-01-05 | Issue Name: About Us Actual Result: The About us button doesn't work. Steps To reproduce: 1. Enter the credential on the login page. HRS ID: 301 password:1234 2. Verify that system should redirect to the Dashboard. 3. Click the profile icon. 5. Click the About Us button. Expected Result: The About Us button should be worked. | Bugs | Functionality Errors | High | Solved | Ridwan |  | After implementing the about us section the about us button should work.
10 | Profile | Apk |  | 2023-01-05 | Issue Name: Not translating in Bangla. Actual Result: All the texts in profile page is not translating in bangla after clicking AZ button. Steps To reproduce: 1. Enter the credential on the login page. HRS ID: 301 password:1234 2. Verify that system should redirect to the Dashboard. 3. Click the profile button on the left top corner. Expected Result: After clicking AZ button all field name should've translated in bangla. | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | After pressing translation button, it should translate every key field name properly.
11 | My Courses | Apk | Emulator | 2023-01-05 | Issue Name: Module name Should be correct Actual Result: In the Dashboard, the Module label name is not accurate Steps To reproduce: 1. Enter the credential on the login page. Id: 301 password:1234 2. Verify that system should redirect to the Dashboard. 3. In the dashboard you will find the module whose name is incorrect Expected Result: The module name should be correct. (My course -> My courses) | Bugs | GUI Error | High | Solved | Ridwan |  | All module names should be in the correct form. Like My Course -> My Courses
12 | My Courses | Apk | Emulator | 2023-01-05 | Issue Name: Progress bar not working Actual Result: In the Refresher training course module course Progress bar not working properly Steps To reproduce: 1. Enter the credential on the login page. Id: 301 password:1234 2. Verify that the system should redirect to the Dashboard. 3. Click My courses 4. Verify that after pressing the My course option It should redirect to the course List. Expected Result: Progress Bar should work properly | Bugs | Functionality Errors | High | Solved | Ridwan |  | My course progress bar not working properly. when I start the course it shows me I already complete 50% of my course.
13 | My Courses -> Refresher training course | Apk | Emulator | 2023-01-05 | Issue Name: Read more about My course description. Actual Result: In the My course Module there is no option to know about the (Refresher training course). Steps To reproduce: 1. Enter the credential on the login page. Id: 301 password:1234 2. Verify that the system should redirect to the Dashboard. 3. Click My courses 4. Verify that after pressing the My course option It should redirect to the Course Module. Expected Result: On the Course List page there needs to be an option About The Course. So that users can know about the course Module. | CR | GUI Error | Low | Solved | Ridwan |  | In the My course Module, there is no option to know about the (Refresher training course). There needs to a button like "About the course" where the users know about the course.
14 | My Courses -> Refresher training course | Apk | Emulator | 2023-01-05 | Issue Name: The button needs to be Visible. Actual Result: The translator's Button Bangla to English is not visible. Steps To reproduce: 1. Enter the credential on the login page. Id: 301 password:1234 2. Verify that the system should redirect to the Dashboard. 3. Click My courses 4. Verify that after pressing the My course option It should redirect to the course List. 5. Enter the Refresher training course module. 6. In the Right corner of the page beside the logout button there is a translator button. Expected Result: The Ban to Eng language translator button should be more visible. | CR | GUI Error | Low | Solved | Ridwan |  | The translator's Button from Bangla to English is not visible. It should visible to the user.
15 | My Courses -> Refresher training course | Apk | Emulator | 2023-01-05 | Issue Name: Button name not translated into Bangla. Actual Result: The download Certificate button does not translate Bangla after pressing the Eng to Ban language option. Steps To reproduce: 1. Enter the credential on the login page. Id: 301 password:1234 2. Verify that the system should redirect to the Dashboard. 3. Click My courses 4. Verify that after pressing the My course option It should redirect to the course List. 5. Enter the Refresher training course module. 6. Press the English to Bangla Language translator Button. Expected Result: The Eng to Ban language translator button should work properly for all the options. | Bugs | Functionality Errors | High | Solved | Ridwan |  | The download Certificate button does not translate Bangla after pressing the Eng to Ban language option.
16 | My Courses -> Refresher training course | Apk | Emulator | 2023-01-05 | Issue Name: The button needs to work properly Actual Result: The download certificate button does not work properly Steps To reproduce: 1. Enter the credential on the login page. Id: 301 password:1234 2. Verify that the system should redirect to the Dashboard. 3. Click My courses 4. Verify that after pressing the My course option It should redirect to the course List. 5. Enter the Refresher training course module. 6. Press the Download certificate Button Expected Result: The download certificate button should work properly. | Bugs | Functionality Errors | High | Solved | Ridwan |  | The download certificate button does not work properly. After pressing the button it should download the certificate.
17 | My Courses -> Refresher training course | Apk | Emulator | 2023-01-05 | Issue Name: Progress bar not working Actual Result: In the Refresher training course module course Progress bar not working properly Steps To reproduce: 1. Enter the credential on the login page. Id: 301 password:1234 2. Verify that the system should redirect to the Dashboard. 3. Click My courses 4. Verify that after pressing the My course option It should redirect to the course List. 5. Enter the Refresher training course module. Expected Result: Progress Bar should work properly | Bugs | Functionality Errors | High | Solved | Ridwan |  | Progress bar not working properly for this couirse.
18 | All Courses -> Refresher training course | Apk | Emulator | 2023-01-05 | Issue Name: Already Enroll. Actual Result: In the All course list, if I am already enrolled in this course the course button name didn't change the name. Steps To reproduce: 1. Enter the credential on the login page. Id: 301 password:1234 2. Verify that the system should redirect to the Dashboard. 3. Click ALL courses 4. Verify that after pressing the All course option It should redirect to the course List. Expected Result: On the all course List page there needs to be a button name "already enroll". So that users can know this course already enrolled. | CR | GUI Error | Low | Solved | Ridwan |  | Button name should change when i am enrolled this course
19 | All Courses -> Refresher training course | Apk | Emulator | 2023-01-05 | Issue Name: Read more about the course description. Actual Result: In the My course Module there is no option to know about the (Refresher training course). Steps To reproduce: 1. Enter the credential on the login page. Id: 301 password:1234 2. Verify that the system should redirect to the Dashboard. 3. Click My courses 4. Verify that after pressing the My course option It should redirect to the Course Module. Expected Result: On the Course List page there needs to be an option About The Course. So that users can know about the course Module. | CR | GUI Error | Low | Solved | Ridwan |  | In all course modules, there needs to be a button name "About the course". After pressing this button you will see the course details and module.
20 | Resource | Apk |  | 2023-01-05 | Issue Name: Spelling Mistake Actual Result: In the dashboard module when AZ button is been pressed the Bangla name of Resources is slightly misspelled. Steps To reproduce: 1. Enter the credential on the login page. HRS ID: 301 password:1234 2. Verify that system should redirect to the Dashboard. 3. Click the AZ button on the right top corner. Expected Result: After clicking AZ button Resources button should've showed রিসোর্স instead of রিসোর্সে. | Fine Tuning | GUI Error | Low | Solved | Ridwan |  | The Bangla translation of a Module should've spelled correctly.
21 | Certificate -> Download Certificate | Apk |  | 2023-01-05 | Issue Name: Not translating in Bangla. Actual Result: Download certificate button is not translating in Bangla after clicking AZ button. Steps To reproduce: 1. Enter the credential on the login page. HRS ID: 301 password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the Certificate button. Expected Result:After clicking AZ button download certificate button should've translated in bangla and should've showed "সনদপত্র ডাউনলোড" | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | After pressing translation button, it should work properly.
22 | Support | Apk |  | 2023-01-05 | Issue Name: Not translating in Bangla. Actual Result: All the texts in support page is not translating in bangla after clicking AZ button. Steps To reproduce: 1. Enter the credential on the login page. HRS ID: 301 password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the support button. Expected Result:After clicking AZ button all texts in the support page should've translated in bangla. | Bugs | Functionality Errors | Medium | Open | Ridwan |  | All text in the support module is already written in Bangla.. when English translation button is selected, Texts are not translating from Bangla to English.
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425